## Sheet1
Not Yet Started | Claimed | In Progress | Ready To Be Tested | In Testing | Complete | Blocked |  | Notes
Sprint 1 - Basic Set Up | [6 empty] | Pat
Create GitHub reopsitory | Pat |  |  |  | Pat |  | Yousef
Import Pat's existing code | Pat |  |  |  | Pat |  | Andy
Research and get working example of multithreading | Mike |  |  |  | Mike |  | Mike
Offline gathering of both .CSV files (and place in repo) | Mike |  |  |  | Mike
Creation of basic text UI | Andy | Andy
Ability to parse through .CSV files and grab players, salaries, avg pts per game, and projected stats | Yousef | Yousef
Calculate a projected score based on Draft King's rules (points are scored slightly differently on ESPN) | Pat
Creation of basic algorithm that gives us SOME result | Pat | Pat | [5 empty] | Just to get something written, I was thinking we could compute all possible lineups that allow you to end up with 0 dollars left in your salary, then pick the lineup that has the most projected points for that week
Test the lineups generated in real world and record results
Polish up UI to display algorithm result
Sprint 2 - Server Work
Research what resources are needed
Get access to private server
Automate pulling of .CSV from Draft Kings
Automate pulling of .CSV from ESPN
Store and retrieve data from server
Increase efficiency of algorithm
Test the lineups generated in real world and record results
Sprint 3 -Porting and Adding Features
Research into Android porting of our code to figure out scope
Port app to Android (break out into smaller tasks once we have done research on scope)
Add feature to allow for manual input of players and have algorithm make a team around those players
Add feature for "safe" or "risky" or "players against weak opponents" lineups
Add feature to show the user top ~3 lineups made, let them choose between them
Test the lineups generated in real world and record results
Prepare final presentation
Profit??????